## RACI Template
[INSERT PROJECT NAME] - RACI template
The RACI is a planning and project management tool that describes and clarifies roles and responsibilities and helps identify who has the final go/no go authority when it comes to making a decision. This tool can help ensure clear and strong communication amongst all stakeholders involved in the project and ultimately make sure no key stakeholders are left out of the decision-making process. A few scenarios when a RACI chart can come in handy: - The decision-making or approval process could hold up the project - There's conflict about task ownership and decision-making The RACI framework helps answer the following questions: 1. WHO is leading the work? WHO is accountable? 2. WHO needs to be directly involved in the work and make decisions? Smart tips to ensure a successful project kick-off using the RACI framework: - Schedule a kick-off meeting with everyone that needs to be involved in the project - Discuss planned roles/responsibilities with each stakeholder to ensure everyone is aligned on the expectations and agrees with the role that they are assigned to - Resolve conflicts and ambiguities by looking both across each row and up and down each column for the following: - Does one stakeholder have too much of the project assigned to them? (i.e. too many R's) - No empty cells: does everyone truly need to be assigned to every single task? Are there "too many cooks in the kitchen"? Directions for using the RACI chart: Step 1: Identify all key functions, tasks and deliverables for the project down the left column Step 2: Identify all key positions and stakeholders who should be involved in the project across the top row Step 3: For each project task identify what each person's level of responsibility is with regard to that particular activity or task
Project task or deliverable | Stakeholders and/or Team
| Team role or name (ex. HR Director) | Team role or name (ex. CFO) | Team role or name (ex. Project manager) | Team role or name (ex. Benefits team) | Team role or name (ex. Finance team) | Team role or name
Ex: Identify solution criteria (i.e. goal) you are trying to solve for | A | C | I | R | C
Ex: Identify budget | R | A | I | C | I
Ex: Develop scorecard for evaluating carriers | A | C | I | R | C
| KEY | R = Responsible | Responsible for performing the task (ie. the actual person doing the work to complete the task). This person or group should identify who needs to be involved, communicate with them and influence others to attain the necessary help, resources and information needed to complete the task. There should always be at least one R assigned for each task.
|  | A = Accountable | Ultimately accountable for the task being done in a satisfactory manner. The accountable person must sign-off the work that the Responsible person produces. For most projects, there will be only one person listed as "accountable".
|  | C = Consulted | Team members whose input is used to complete the task. This person or group should be consulted in the early stages of a project to enhance decision quality and/or establish buy-in. Communication with this person or group should be 2-way nature. Ideally you want to keep the number of C's to a minimum for each task. Having too many consultants can slow down the process.
|  | I = Informed | Team members who are informed as to the status of the task. Communication with these members will be 1-way in nature. There can be as many I's as necessary per task.

## Scorecard Template
Carrier evaluation scorecard
What is a scorecard used for?
This scorecard is a designed template specifically used to help organizations make better, faster and more cost-effective decisions when comparing multiple health insurance carriers. More than using this as a comparison tool, this scorecard can also help your organization identify which categories/components of a health insurance plan are most important to your organization simply based on how you rate each one.
Who can take advantage of this scorecard?
Any organization evaluating and purchasing health insurance benefits for their employees.
Executives seeking to understand the vendor decision making methodologies
Project teams faced with vendor selection initiatives
How to use this scorecard:
Key stakeholders involved in the decision making process should align on the categories and any sub-categories that you want to compare each vendor against. Each category should receive a % weighting - meaning from 0-100% how important is it to you and your organization that these items be included in your benefits package.
Rate your current carrier using the 0-4 scale for each of these categories/sub-categories. It's important to upfront align on what 0-4 means - without having clear definitions of what quantifies a 0 score vs. 4 makes the scoring that much more subjective across team members and may cause tension/misalignment later on when it comes to making a final decision
The score of your current carrier can help you determine which questions to go back to your agent to discuss to ensure the proposals you are getting from new vendors include these items that you are ranking most important to your organization
The sections and sub-sections below are completely customizable, but we've provided you with some examples to start thinking through based on what your current carrier offers
Rating | Scoring Value | Definition
Superior | 4 | Proposal exceptionally exceeds performance or capability requirements; proposal demonstrates extraordinary strengths that will more than significantly benefit us
Exceeds | 3 | Proposal exceeds performance or capability requirements; proposal has one or more strengths that will benefit us
Meets | 2 | Meets specified minimum performance or capability requirements necessary for acceptable contract performance.
Meets with Exceptions | 1 | Proposal demonstrates weak performance or capability standards necessary for minimum contract performance; proposal has one or more weaknesses that offset any strengths.
Does Not Meet | 0 | Fails to meet specified minimum performance or capability requirements. Proposals with an unacceptable rating are not awardable.
Evaluation Categories | % Weighting | Current Vendor (Example) |  | Vendor A |  | Vendor B |  | Vendor C
|  | Rate | Score | Rate | Score | Rate | Score | Rate | Score
Financial security and quality awards | 5% |  | 0.55 |  | 0 |  | 0 |  | 0
Financial rating |  | 4 | 0.2 |  | 0 |  | 0 |  | 0
CMS score(s) |  | 4 | 0.2 |  | 0 |  | 0 |  | 0
NCQA Accreditation |  | 3 | 0.15 |  | 0 |  | 0 |  | 0
Customer service | 10% |  | 0.8 |  | 0 |  | 0 |  | 0
Customer service performance (hours, awards, navigation capabilities, first call resolution) |  | 4 | 0.4 |  | 0 |  | 0 |  | 0
Local representatives available |  | 4 | 0.4 |  | 0 |  | 0 |  | 0
Member benefits | 25% |  | 2.5 |  | 0 |  | 0 |  | 0
Cost transparency tool |  | 2 | 0.5 |  | 0 |  | 0 |  | 0
Rewards program |  | 2 | 0.5 |  | 0 |  | 0 |  | 0
Member app and/or virtual ID card |  | 0 | 0 |  | 0 |  | 0 |  | 0
Gym discount program |  | 2 | 0.5 |  | 0 |  | 0 |  | 0
Wellness program/resources |  | 0 | 0 |  | 0 |  | 0 |  | 0
Nationwide network access |  | 4 | 1 |  | 0 |  | 0 |  | 0
Travel assistance |  | 0 | 0 |  | 0 |  | 0 |  | 0
Premium or admin fee | 15% |  | 0.9 |  | 0 |  | 0 |  | 0
% savings offered |  | 3 | 0.45 |  | 0 |  | 0 |  | 0
Rate guarantee (2 year, 3 year?)
Vendor partners available at no additional cost |  | 3 | 0.45 |  | 0 |  | 0 |  | 0
Care management programs | 10% |  | 0.9 |  | 0 |  | 0 |  | 0
No fee for access to care management |  | 2 | 0.2 |  | 0 |  | 0 |  | 0
Local care managers |  | 3 | 0.3 |  | 0 |  | 0 |  | 0
No limit on members enrolled in program |  | 2 | 0.2 |  | 0 |  | 0 |  | 0
Self-directed or member assisted online care management programs (i.e. Omada Diabetes Prevention Program) |  | 2 | 0.2 |  | 0 |  | 0 |  | 0
Implementation | 5% |  | 0.3 |  | 0 |  | 0 |  | 0
Dedicated implementation specialist |  | 3 | 0.15 |  | 0 |  | 0 |  | 0
Customized implementation timeline |  | 3 | 0.15 |  | 0 |  | 0 |  | 0
Administrative ease | 30% |  | 3.6 |  | 0 |  | 0 |  | 0
Online employer account for self-service |  | 3 | 0.9 |  | 0 |  | 0 |  | 0
Comprehensive reporting |  | 2 | 0.6 |  | 0 |  | 0 |  | 0
Local account manager/account management team |  | 3 | 0.9 |  | 0 |  | 0 |  | 0
Member onboarding and education |  | 2 | 0.6 |  | 0 |  | 0 |  | 0
Open enrollment support |  | 2 | 0.6 |  | 0 |  | 0 |  | 0
Total Score | 100% |  | 9.55 |  | 0 |  | 0 |  | 0
Note on W1: Garbarino, Kristine M.: Everything on this template looks good. Can we just have it saved so that it opens at 100% when the user downloads/opens it? Can we also fix the page breaks in case someone wants to print this out?